## Change log
PROJECT CHANGE LOG - OVERVIEW
Project Name: |  |  |  | Project Sponsor:
Project Manager: |  |  |  | Last revised:
Project Objective:
Change ID |  | Change description | Requested by | Request date | Summary of cost impacts | Summary of schedule impacts | Status
SUMM. 01 | 1 | Change description 01 | Steve | 2018-07-05 | No relevant impacts on project costs. | Delay of two weeks on tasks 3.4 and 3.5 (see WBS for a detail description of the tasks) | Formally approved
| 2 | Change description 02 | John | 2018-07-06 | Increases task 2.1 projected costs by 20% while reducing task 2.3 costs by 10%. Net total cost increase of 2%. | Reduction of 3 weeks on overall project schedule. | Recommendation Issued
| 3 | Change description 03 | Michael | 2018-07-08 |  |  | Recommendation Issued
SUMM. 02 | 4 | Change description 04 | Michael | 2018-07-12 |  |  | Being Discussed
| 5 | Change description 05 | Michael | 2018-07-14 |  |  | In Queue
| 6 | Change description 06 | John | 2018-07-15 |  |  | In Queue

## Change log documents
PROJECT CHANGE LOG - DOCUMENTS
Project Name: |  |  | Project Sponsor:
Project Manager: |  |  | Last revised:
Centralized document repository: [INSERT FOLDER LINK]
Change ID |  | Document title | Document link
SUMM. 01 | 1 | Document title 01 | [INSERT DOCUMENT LINK]
| 2 | Document title 02 | [INSERT DOCUMENT LINK]
| 3 | Document title 03 | [INSERT DOCUMENT LINK]
SUMM. 02 | 4 | Document title 04 | [INSERT DOCUMENT LINK]
| 5 | Document title 05 | [INSERT DOCUMENT LINK]
| 6 | Document title 06 | [INSERT DOCUMENT LINK]